Project Title: Enhancing Livelihood Resilience for Tribal Self-Help Group Women in Bingaon Area, Dist. Khunti, Jharkhand, India

Submitted to:

Ananad Bhavan, Arnhem

Netherlands

Submitted by:

RANCHI JESUITS

Ranchi, Jharkhand

PROJECT DETAILS

| Project Title | Enhancing Livelihood Resilience for Tribal Self-Help Group Women in Bingaon Area, Dist. Khunti, Jharkhand, India |
| --- | --- |
| Project Location | Bingaon, Block Karra, District Khunti, Jharkhand, India |
| Name of the Organization | Ranchi Jesuits |
| Address | SADBHAVNA, Jesuit Provincial’s Residence, Dr. Camil Bulcke Path, P.O. Box 4, Ranchi, JHARKHAND – INDIA. |
| Responsible person | Fr. George Kerketta, SJ Sadbhavna, Dr. Camil Bulcke Path, Ranchi – 834 001, India Tel.: +91-651 2215479 Mobile Phone: +91-9431106878 Email: georgekerkettasj@gmail.com |
| Project Cost | Rs. 9,30,000 (EUR 10,333) |
| Fund Requested | Rs. 9,00,000 ( EURO 10,000) |
| Project Duration | 12 Months |
| Date of Submission | 10 October 2024 |

1. INTRODUCTION

1.1. About the project:

This project aims to empower rural women farmers in the Ranchi region by improving agricultural practices and increasing income-generation opportunities through the formation and strengthening of 10 Self-Help Groups (SHGs). Focused on promoting organic vegetable cultivation, cash crops like ginger and turmeric, and the plantation of 1,000 fruit trees, the project seeks to address challenges such as low agricultural productivity, reliance on rain-fed farming, and limited access to markets. By providing training and resources to SHG members, the initiative aligns with the Ranchi Jesuits' mission of uplifting marginalized communities, promoting sustainable livelihoods, and fostering environmental stewardship.

1.2. About the Implementing Agency-Ranchi Jesuits:

Ranchi was the part of Bengal mission (Calcutta Province) for many years. In 1935 the Ranchi Mission gained an identity of its own, separate from the Calcutta Mission with Fr. Charles Timmerman, as the first Mission Superior. Later it became Vice Province. It became a full-fledged Jesuit Province in 12th March 1956. Now it has become a vibrant province in South Asian Assistancy with more than 382 Jesuits working in India and abroad. It is serving the tribal community by running 2-degree colleges, 1 Management Institution, One Technical Institute, 7 Junior Colleges, 22 high schools, 27 Middle schools and 38 Primary schools in most interior places for Adivasi. Ranchi Jesuit Society is educating 53,915 (2016) through these educational Institutions. It is also running 29 parishes in Ranchi, Assam and Andaman and Nicobar Islands. Some of the schools are attached to these parishes. It has 6 social service centers to cater to the need for socio-economic development of the Adivasi people. The proposed project proposal is for the Munda Tribal children in most backward areas where even the Belgian early missionaries in the 19th century found a tough and unproductive mission field as far as mission activities and results were concerned so abandoned this area for more than 100 years.

Over a period of time, the Ranchi Jesuit Mission has effectively worked towards empowering the educational standard of children in the school belonging to the poor irrespective of caste and creed with limited infrastructure and facilities. Along with that, the Jesuits have carried out various developmental activities such as agriculture, animal husbandry, forestry, etc with the villagers in order to uplift their economic situation. The activities received wide appreciation and support from the communities.

1.3. About the Bingaon Parish:

Bingaon parish was established in 1987 in Khunti district, Jharkhand, near the border with Ranchi district. It falls under Khunti Diocese and is home to 707 Catholic families with a population of 3,535. The parish comprises 35 villages and 12 village chapels/centers. There is an RC Middle School on the church campus with 377 students under the guidance of 8 teachers and 1 priest. Additionally, a boys' hostel accommodates 19 children from remote villages. Mundari and Hindi are the prevalent languages in the parish, which faces challenges in accessing basic facilities and dignified living for tribal populations, especially the Munda tribe. The concentration of tribal population in the parish is very high. The condition of STs and SCs is not very good and they are still struggling for their basic rights and dignified life. They are excluded from the mainstream development paradigm and basic facilities required for dignified life which perpetuate their problems and ultimately their exclusion continued in spite of many efforts.

2. PROJECT AREA

2.1 Geography

The project area is located in Karra Block, which is an administrative block in the Khunti district of Jharkhand. The district shares boundaries with West Singhbhoom, Saraikela Kharsawan, Gumla, and Simdega. The climate in the district is subtropical semi-arid, with an annual rainfall of about 1057.12 mm. The area covers 2535 square kilometers, characterized by undulating hills, forests, and diverse soil textures. Forest cover accounts for 35% of the geographical area, comprising very dense, moderately dense, and open forests. This forested land consists of very dense, moderately dense, and open forests, contributing to the region's biodiversity and environmental significance.

2.2. About the people

The Bingaon parish falls under a rural area characterized by its natural surroundings. In this region, the tribal community outnumbers the Muslim and Dalit populations. In the tribal community, Oraon and Munda are the main tribal communities residing in the parish. The majority of the population is Christian in the parish, while a significant number of the population belong to the Sarna religion. The local population mainly falls under the category of Below Poverty Line (BPL). The primary occupations include farming, labor work, semi-skilled labor, fruit, and vegetable vending, as well as running small shops. Due to its proximity to the city of Ranchi, the parish experiences a notable level of migration to the city in search of employment opportunities. Many parents of the parish prefer to enroll their children in government or aided schools, as they find it challenging to afford the expenses associated with education.

2.3. Socio-economic situation of the people

The people of the area depend on rain-fed agriculture for their livelihood. The failure of the monsoon or scanty rainfall directly affects their economic condition. The outdated system of agriculture affects the yield. The area is good for the cultivation of lac but due to marketing and other challenges involved in the production of quality lac the farmers are not able to make the most out of the possibility. The depleted forest too does not provide them with supplementary income. The village markets are in the clutches of the business class who do not give a just price to the home products. Thus, poverty is rampant in the area and the economic condition of the people is deplorable. The government schemes reach them in bits and pieces as the intermediaries pocket most of them. The area has no industry or factory to get labour and therefore many of them go to markets for daily work if available or migrate to cities to earn their livelihood.

2.4 Education

In Bingaon Parish, education is provided through four main schools, with Prabhat Middle School Bingaon and St. Anne's G.T.D.M High School Kachabari being the prominent institutions. However, the region grapples with a concerning dropout rate, with approximately 10% of students leaving school due to financial constraints. This issue underscores the urgent need for targeted interventions to alleviate economic burdens on families, ensuring that children have unhindered access to education. Education support, scholarships, subsidies, and community-driven initiatives could serve as vital tools in combating this challenge and fostering a more conducive learning environment for the youth of Bingaon Parish.

2.5. Health

The people of the Bingaon parish face significant challenges, primarily due to malnutrition, which renders them vulnerable to various diseases. Malnourishment weakens the immune system, making individuals more prone to infections and illnesses. This health issue is further compounded by the fact that the area is prone to malaria. Throughout the year, people in Bingaon are frequently afflicted by malaria, remaining in its grip persistently.

The healthcare infrastructure in Bingaon is limited, with a few primary health centers and private medical practitioners working in the area. Apart from it, there are no major health facilities or hopitals in the parish. As a result, many residents prefer to seek medical attention at hospitals located in nearby areas such as Khunti and Ranchi, where better check-up facilities and more specialized care are available.

3. PROBLEM STATEMENT

The Ranchi Jesuits have long been committed to serving marginalized communities and promoting faith, justice, and reconciliation as part of their Apostolic Plan and Universal Apostolic Preferences. However, in the rural areas of Ranchi, especially in the villages in Bingaon parish, there is a growing concern about the persistent issues of poverty, lack of education, and low agricultural productivity. These communities are heavily reliant on agriculture for their livelihoods, yet they face significant challenges due to limited access to resources, outdated farming techniques, and their dependency on unpredictable monsoons.

The farmers’ agricultural productivity is hampered by several factors:

- Farmers in these rural areas lack proper tools, technology, and financial resources to improve their farming methods. This limitation reduces their ability to invest in seeds, fertilizers, irrigation systems, and better farming practices.

- The agrarian economy in these villages is largely rain-fed, making it highly vulnerable to climate variability. Unpredictable and erratic rainfall patterns often result in crop failure, low yields, and food insecurity.

- The communities also suffer from a lack of access to quality education, which hinders overall development. Without proper education, it becomes difficult for individuals to seek alternative employment, adopt modern farming techniques, or understand sustainable agricultural practices.

- Due to poor agricultural output and a lack of alternative income sources, poverty is widespread in these villages. Families struggle to make ends meet, with little opportunity for economic advancement.

These interconnected issues have led to a vicious cycle of poverty, low productivity, and limited opportunities for the people in these rural areas. The Jesuits recognize that without significant intervention, this cycle will continue to keep the community marginalized, isolated, and underdeveloped.

Proposed Intervention:

In response to these challenges, the Ranchi Jesuits have decided to intervene by empowering the local community through Self-Help Groups (SHGs) that focus on sustainable agriculture, plantation, and the promotion of cash crops. The objective is to improve agricultural productivity, diversify income sources, and build the economic resilience of these communities.

By empowering SHGs, the project aims to foster community-driven development. SHGs will provide a platform for collective savings, access to microcredit, and skill-building workshops, allowing community members to pool resources and support one another in their agricultural ventures.

This initiative aligns with the core values of the Ranchi Jesuits, as it not only addresses the economic and social issues faced by the rural community but also promotes integral human development in line with their broader mission of faith, justice, and reconciliation. Through this project, the Jesuits hope to create a sustainable model for rural development that can be replicated in other regions facing similar challenges.

4. TARGET GROUPS

The target group consists of women from 10 Self-Help Groups (SHGs) belonging to tribal communities in Bingaon Parish, Jharkhand, India. The total population of the target group is around 100 women. They represent diverse demography with a predominant tribal background, specifically the Munda tribe. Socially, they face challenges related to poverty, lack of education, and exclusion from mainstream development. Cultural issues arise from their traditional way of life and limited exposure to modern practices. Economically, they struggle with low agricultural productivity, insufficient access to credit and markets, and limited diversified income sources beyond agriculture. The project aims to address these issues and empower women for sustainable development and improved livelihoods.

5.  PROJECT OBJECTIVES

The main purpose of the project is to enhance agricultural practices and income generation opportunities for farmers in the target area through 10 SHGs.

Specific Objectives of the Project:

- To promote organic vegetable cultivation

- To provide support for paddy cultivation

- To promote ginger and turmeric cultivation as cash crops

- To provide training on organic farming and organic manure production.

- To install two organic manure production units

- To promote 1000 fruit tree plantation

6. ACTIVITIES

The proposed project will have the following activities,

- Cultivate vegetables through organic cultivation methods. The process begins with identifying SHG members who are interested in vegetable cultivation, focusing on those who would benefit from receiving vegetable seeds like tomatoes, spinach, and brinjal. Once the beneficiaries are identified, high-quality seeds will be procured from certified suppliers to ensure good germination and yield. These seeds will then be distributed in villages, ensuring that each SHG member receives an adequate quantity. During the distribution, a brief training session will be conducted to educate the participants on proper sowing techniques, organic pest control methods, and the overall benefits of maintaining kitchen gardens.

- Paddy cultivation: SHG members practicing paddy farming will be identified based on their landholdings and current farming practices. High-quality, drought-resistant paddy seeds will be procured and distributed to them.

- Cultivate ginger and turmeric cultivation to boost cash crop production. SHG members who express interest in cultivating cash crops will be identified for the distribution of ginger and turmeric seeds. High-value seeds for these crops will be procured from reliable sources. Once obtained, the seeds will be distributed to the selected SHGs.

- Plant 1000 fruit trees (guava, mango, jackfruit, banana, lemon). High-quality saplings will be procured from a certified nursery to ensure optimal growth and yield. Once purchased, these saplings will be distributed to SHG members.

- One village-level training on organic farming: A village-level training will be organized, focusing on essential topics such as why organic farming, organic pest control, crop rotation, and composting techniques. A qualified expert in organic farming will be selected to facilitate the training session.

- Installation of Two Organic Manure Production Units (Demonstration): Necessary materials, including compost bins and tools, will be acquired to establish organic manure production units. To facilitate hands-on learning, two demonstration units will be set up in villages, allowing SHG members to observe the process and gain practical insights into organic manure production.

- Procurement of Organic Manure for Initial Cultivation: Organic manure (cow dung compost or vermicompost) will be purchased to support the initial cultivation phase. Organic manure will be distributed to needy SHG members along with guidance on its use in vegetable and cash crop farming.

- Village-Level Training on Organic Manure Production: A training session will be conducted for SHG members by an expert, explaining how to produce organic manure using locally available resources.

7. OUTPUTS

- 100 SHG women will receive vegetable seeds for kitchen gardens.

- 50 SHG farmers will receive paddy seeds.

- 50 SHG farmers will receive ginger and turmeric seeds.

- 100 fruit tree saplings will be distributed among SHG women.

- 2 organic manure production units will be installed and demonstrated in the villages.

- 1 village-level training on organic farming with 100 participants.

- 1 village-level training on organic manure production with 100 participants.

- SHG members will receive sufficient organic manure to initiate organic farming practices.

8. OUTCOMES

- The use of quality seeds and organic farming techniques will increase agricultural productivity among SHG members.

- SHG members cultivating high-value crops like ginger and turmeric will generate higher incomes through diversified income sources.

- Adoption of organic farming and organic manure production techniques will improve soil health, reduce chemical usage, and enhance the long-term sustainability of farming in the region.

- Vegetable seeds and fruit tree saplings will provide additional food sources for SHG households, improving their nutrition and food security.

9. IMPACTS:

The project will have a positive impact on the livelihoods and well-being of SHG women and their communities. By increasing agricultural productivity through the use of quality seeds and organic farming techniques, the initiative will contribute to poverty reduction and improved food security. The cultivation of high-value crops like ginger and turmeric will diversify income sources, boosting household incomes and economic resilience. Environmentally, the adoption of sustainable farming practices and organic manure production will promote soil health and reduce reliance on harmful chemicals, fostering long-term environmental sustainability. Socially, the project will empower women by strengthening SHGs, giving them a collective voice and better access to resources and decision-making processes. The successful implementation of these activities in Bingaon Parish can serve as a model for similar interventions in other rural areas, allowing for scalability and replication in addressing agricultural and livelihood challenges.

10. PROJECT TIMELINE

Depending on the approval of the project and the availability of funds, the project will be completed in 12 months. Final reporting to the donor will be done in the 13th month of the project.

| Activities | Months |  |  |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 |
| Vegetable cultivation |  |  |  |  |  |  |  |  |  |  |  |  |
| Paddy cultivation |  |  |  |  |  |  |  |  |  |  |  |  |
| Ginger and Turmeric cultivation |  |  |  |  |  |  |  |  |  |  |  |  |
| Fruit tree plantation |  |  |  |  |  |  |  |  |  |  |  |  |
| Install Two Organic Manure Production Units |  |  |  |  |  |  |  |  |  |  |  |  |
| Village-level training on organic farming |  |  |  |  |  |  |  |  |  |  |  |  |
| Village-level training on organic manure production |  |  |  |  |  |  |  |  |  |  |  |  |

11. MONITORING, EVALUATION AND REPORTING AND FOLLOW-UP PLANS

The project will be implemented by the Bingaon parish under the leadership of the parish priest. A project team under the supervision of the Province Development Director (PDD) will look after the project. The Province Development Director, Ranchi will regularly follow up on the progress of work in consultation with the local lead person. The PDD will be responsible to prepare progress report, final report, and financial report of the project; and updating the donor as per the timeline.

12. ESTIMATED BUDGET:

| S.N. | Particulars | Unit cost | No. of units |  | Amount in INR | EUR |
| --- | --- | --- | --- | --- | --- | --- |
| PART-A: PROGRAMME COST |  |  |  |  |  |  |
| 1 | Vegetable Seeds | LS |  |  | 250000 | 2,778 |
| 2 | Paddy seeds | LS |  |  | 100000 | 1,111 |
| 3 | Ginger seeds | LS |  |  | 100000 | 1,111 |
| 4 | Turmeric seeds | LS |  |  | 65000 | 722 |
| 5 | Fruit tree saplings | 150 | 1000 |  | 150000 | 1,667 |
| 6 | One village-level training on organic farming (Banner, training materials, refreshments, Trainer's fee) | LS |  |  | 20000 | 222 |
| 7 | Procure materials for installing two organic manure production units for demonstration in villages | 20000 | 2 |  | 40000 | 444 |
| 8 | Procure organic manure for initial cultivation | LS |  |  | 50000 | 556 |
| 9 | One village-level training on Organic manure production (Banner, training materials, refreshments, Trainer's fee) | LS |  |  | 20000 | 222 |
| 10 | Transportation cost for seeds/saplings/items procurement and distribution in villages | LS |  |  | 15000 | 167 |
|  | Subtotal (A) |  |  |  | 8,10,000 | 9,000 |
| PART-B: MANAGEMENT COST |  |  |  |  |  |  |
| 5 | Project Coordinator (PC) | 5000X 12 | 1 |  | 60,000 | 667 |
| 6 | One Field Supervisor (FS) | 3000 X12 | 1 |  | 36,000 | 400 |
| 7 | Traveling of PC & FS | 2,000 X 12 |  |  | 24,000 | 267 |
|  | Subtotal (B) |  |  |  | 1,20,000 | 1333 |
|  | Grand Total |  |  |  | 9,30,000 | 10,333 |
| FINANCIAL PLANNING |  |  |  |  |  |  |
|  |  | Amount (INR) |  | Amount (EURO) |  |  |
| 1 | Local contribution | 30,000 |  | 333 |  |  |
| 2 | Fund requested | 9,00,000 |  | 10,000 |  |  |
|  | Grand Total | 9,30,000 |  | 10,333 |  |  |

Conversion rate @ EUR to INR =Rs. 90

Note: Local contributions will be made by the Ranchi Jesuits, Bingaon Parish and others.

Hence, the project would like to request a grant of Rs. 9,00,000 or EURO 10,000.

Declaration:

I hereby solemnly affirm and declare, with utmost honesty and transparency, that up to this point in time, no project application whatsoever has been submitted or presented in any capacity, either formally or informally, to any individual, organization, or authority for the implementation of the project specified above. This declaration serves as an unequivocal statement of the current status of the project, and I affirm that no prior attempts have been made to seek approval, funding, or support from any relevant parties or entities.

Fr. Geroge Kerketta SJ.

Province Development Director, Ranchi Jesuits

Ranchi